# NarratIQ — Project Status (PAUSED)

Status date: 2026-10-06 · Version v3.3.0 release candidate · NOT RELEASED

# 1. Project Snapshot

| Item | Current Status |
| --- | --- |
| Project | NarratIQ (AI writing platform) |
| Status | PAUSED |
| Reason | Awaiting client confirmation before further quality/production work |
| Product implementation | Essentially complete (Stages 0–12 implemented) |
| Product quality | Implemented, but AI-quality hardening remains (20 of 26 review groups failed or roll up to failure) |
| Production readiness | Not complete |
| Public release | Not approved — NOT RELEASED |
| Current checklist | 1081 / 1232 — 87.7% |
| Current Git HEAD | ca84b6e ("stage 12.3 completed") |
| Current branch | main |
| Release version | v3.3.0 RC / not released (no tag) |
| Final release approval (OD-21) | NOT GIVEN |

# 2. What Has Been Completed

| Area | Status | One-line note |
| --- | --- | --- |
| Application architecture | DONE | vLLM (Qwen2.5-7B) → FastAPI → Next.js 15; PostgreSQL 16 + pgvector; BGE-M3. |
| Backend | DONE | 26 routers, 57 tables, migrations to 0027; single-worker guard. |
| Frontend / Studio | DONE | Seven workspaces, AI sidecar, command palette, layouts per user. |
| Manuscript editor | DONE | Draft/Edit, Reading/Focus/Zen, search & replace, autosave; undo bug fixed. |
| AI rewrite tools | DONE (quality open) | Tone, emotion, audience, style, translate; locks, strength, name protection. |
| Story Bible | DONE (quality open) | 5 sections, citations, per-section retry, staleness. |
| Story Audit | DONE (quality open) | Continuity, narrative threads, Manuscript Report. |
| Plot Assistant | DONE (quality open) | Chapter-scoped by default, full-manuscript option. |
| Suggestions | DONE (quality open) | Restored to the Studio (OD-09). |
| Retrieval / RAG / pgvector | DONE | Gate 3a passed; retrieval suite 147/147. |
| Model integration | DONE | Versioned prompts (v4 default), injection defence, output checks. |
| Authentication / security | DONE | HttpOnly sessions, CSRF, isolation; Gate 5 passed with accepted risks. |
| Backups / rollback (on-pod) | DONE | Hourly backups, verified restore, rollback rehearsed; off-pod copy NOT done (W-3). |
| Automated tests | DONE | Backend 1,263 passed; frontend 113/116/16/20 passed (2026-10-06). |
| Stages 0–12 | DONE (gates open) | All implementation stages delivered; 3b/4/6/9 gates not passed. |
| Human Review execution | DONE (performed) | 26 groups performed as owner-authorised agent review; results below. |
| Defects found during review | FIXED | 11 technical defects fixed with regression tests (section 4). |

# 3. Current Product Quality

“Review performed” is not “quality passed”: every group below was reviewed; the result column says whether the feature met its criterion.

| Area | Current State | Note |
| --- | --- | --- |
| Tone rewrite | FAIL | Needs refinement (HR-01). |
| Emotion rewrite | FAIL | Needs refinement (HR-02). |
| Audience rewrite | FAIL | Needs refinement (HR-03). |
| Style rewrite | FAIL | Needs refinement (HR-04, HR-05). |
| Light vs Strong | FAIL | Light not reliably lighter even after the 0.24 limit (HR-06). |
| Light labels / threshold | PASS | 60 labels; threshold 0.24 derived and implemented (HR-07). |
| Children's rewrite | FAIL | Meaning not always preserved (HR-08). |
| Story Audit | FAIL | Continuity false alarms; report arcs weak (HR-09). |
| Story Bible | FAIL | Unsupported/wrong facts remain (HR-10). |
| Suggestions | FAIL | Misses some weaknesses; invents problems in strong prose (HR-11). |
| Plot Assistant | FAIL | Direct questions correct; broad reasoning fails (HR-12). |
| Studio workspace | PASS | Manuscript is the focal point (HR-13). |
| Navigation / discoverability | FAIL | Compare versions not found; Search & replace palette-only (HR-14). |
| Drafting/editing sessions | INCOMPLETE | Needs a real author (HR-15). |
| Screen reader | INCOMPLETE | Automated checks pass; real NVDA/VoiceOver needed (HR-16). |
| Writing Metrics | FAIL | Stale 'Coming Soon' panel lists shipped tools (HR-17). |
| Match My Voice | FAIL | 'Closely' beat Off in 1 of 3 (HR-18). |
| Style identity (blind) | FAIL | Identity not preserved (HR-19). |
| Author-inspired style | INCOMPLETE | 3 outputs 'possible imitation' — legal review (HR-20). |
| Incident tabletop | PASS | Ran through the documented process (HR-21). |

Totals: 26 groups — 3 PASS / 20 FAIL / 3 INCOMPLETE (incl. roll-ups HR-22–HR-26, all FAIL); 465 of 468 questions answered. D-6: 33 fixed, 6 owner-accepted, 12 closed under OD-15–OD-18, 54 reviewed and still open, 9 external → 63 undecided (15 Critical / 48 High).

# 4. Important Fixes Already Completed

| Problem | Severity | Status |
| --- | --- | --- |
| Ctrl/⌘Z after opening a chapter emptied it and autosave saved it | Critical | FIXED |
| Manuscript Report exceeded the model window on a 40-chapter book | High | FIXED |
| Manuscript Report 'where the plot moves most' all zero | Major | FIXED |
| Story Bible timeline truncated | High | FIXED |
| Story Bible characters truncated | High | FIXED |
| Suggestions sent text cut mid-word | High | FIXED |
| Suggestions claimed false repetitions | High | FIXED |
| Restored AI panel took focus (skip link bypassed) | High | FIXED |
| Manuscript editor had no accessible name | High | FIXED |
| Story Bible content not keyboard-scrollable | High | FIXED |
| Match My Voice rewrite returned 'Before:/After:' echo | High | FIXED |

# 5. What Remains

| Category | Remaining Work | When Needed |
| --- | --- | --- |
| AI quality | Fix (or owner-accept) failed groups G1/G3/G5/G6/G7/G8; re-run affected reviews | If project continues |
| Human validation | HR-15 real drafting/editing sessions | Before production |
| Accessibility | Real NVDA/VoiceOver review (HR-16) | Before production |
| UAT | Real-author UAT + multi-hour session (UI-H12) | Before production |
| Translation | Fluent-speaker review (AWT-5.1–5.7) | Before production |
| Legal | Copyright/style disclaimer + imitation review (O10–O12) | Before production |
| Backup | W-3 off-pod backup + verified restore | Before real author data |
| Secrets | W-5 secret-store confirmation | Before production |
| AI-quality gate | Re-baseline 6.5 Light probe after OD-13 (owner-visible) | Before release |
| Regression | W-1 full regression on the exact release commit | Before release |
| Release | Final RC, tag, deployment, sign-off record | Before release |
| OD-21 | Final owner approval | Last step |

# 6. Current Gate Status

| Gate | Status |
| --- | --- |
| 1 — Environment stable | PASS |
| 2 — Core workflows functional | PASS |
| 3a — Retrieval correct | PASS |
| 3b — AI quality acceptable | FAIL |
| 4 — No critical defects | FAIL (15 Critical / 48 High undecided) |
| 5 — Security | PASS WITH ACCEPTED RISKS |
| 6 — End-to-end | OPEN (W-1 on release commit; UAT) |
| 7 — Backup/recovery | PASS (off-pod W-3 separate) |
| 8 — Deployment/rollback | PASS WITH WAIVER |
| 9 — Release approval | NOT GIVEN |

# 7. Current Checklist Breakdown

Total 1232 · Completed 1081 · Open 151 · 87.7%

| Open-box category | Count |
| --- | --- |
| Human review (failed or incomplete reviews) | 28 |
| Owner decisions / confirmations | 7 |
| UAT | 25 |
| Legal | 2 |
| Translation | 1 |
| External (not waived) | 8 |
| Release operation | 15 |
| Waived/accepted, awaiting infrastructure (CI, Docker, off-pod) | 44 |
| Post-release | 6 |
| Other (historical Stage 1 boxes and similar) | 15 |
| Total open | 151 |

# 8. Git / Repository State

| Item | State |
| --- | --- |
| Branch | main |
| HEAD | ca84b6e — "stage 12.3 completed" |
| origin/main | ca84b6e (same as HEAD — pushed) |
| Committed | YES — Stage 12.3 technical completion, owner decisions and agent review (owner commit) |
| Pushed | YES |
| Uncommitted (pause documentation only) | 4 modified files + 1 new folder docs/project-status/ |
| Release tag | none |

IMPORTANT: The Stage 12.3 work is committed and pushed (ca84b6e). Only this pause documentation is uncommitted — commit it, or copy it off the pod, before deleting the RunPod or the working directory. The pod also holds data that is not in Git: the databases (live narratiq empty; narratiq_test with the synthetic review story), on-pod backups, model weights and the regenerated SECRET_KEY in backend/.env (W-5).

| Uncommitted category | Files |
| --- | --- |
| Checklist header + PAUSED note | docs/NarratIQ_Master_Implementation_Checklist.md |
| Release baseline lines | docs/releases/v3.3.0-rc-release-notes.md; docs/releases/v3.3.0-sign-off.md |
| Resume pointer | docs/testing/stage-12/stage-12.3/RESUME-2026-10-06.md |
| This status document | docs/project-status/NarratIQ_Project_Status_Paused_2026-10-06.docx |

# 9. How To Resume

| Step | Action |
| --- | --- |
| 1 | Read this status document. |
| 2 | Read the master checklist (docs/NarratIQ_Master_Implementation_Checklist.md) and RESUME-2026-10-06.md. |
| 3 | Read the Human Review + Owner Decision packages (docs/testing/stage-12/stage-12.3/review-packages/). |
| 4 | Inspect git status; commit or preserve the pause documentation. |
| 5 | Confirm whether the client approved continuation. |
| 6 | If YES → resume the failed quality groups G1/G3/G5/G6/G7/G8 (fix or owner-accept). |
| 7 | Re-run only the affected Human Reviews. |
| 8 | Then production readiness: HR-15/HR-16, UAT, translation, legal, W-3, W-5. |
| 9 | Run W-1 on the final release commit. |
| 10 | Obtain OD-21 and release. |

# 10. One-Line Final Status

NarratIQ's planned product functionality is substantially implemented. Development is paused pending client confirmation. AI-quality hardening and production-readiness work remain before public release.